ClubSphere

University Club & Activity Lifecycle Management System

Two-Person Project Execution and Work Distribution Plan

Team: Aryan & Vanshika

Document version 1.0 — Draft, dates pending confirmation

# Table of Contents

# 1. Milestone Schedule

⚠ Date confirmation required: the milestone screenshot uses relative labels ('@Last Thursday', '@Next Monday') rather than fixed dates. The resolution below is a tentative assumption based on the screenshot's own timestamp (captured Monday, Oct 12, 2026) and MUST be confirmed with the project lead/faculty before being treated as final.

| Milestone | Date (as given / resolved) | Deliverable | Reviewed by | Status |
| --- | --- | --- | --- | --- |
| Registration closes | Last Thursday -> tentatively Thu, Oct 8, 2026 (CONFIRM) | Registration form with accepted undertaking | Project lead | To verify |
| Design review | Next Monday -> tentatively Mon, Oct 19, 2026 (CONFIRM) | Design document, ER diagram, threat model | System Design & RDBMS faculty | To verify |
| Mid review | Wed, Oct 28, 2026 (fixed) | Repository link + one core feature working end to end | Mentor | Fixed |
| Security check | Tue, Nov 3, 2026 (fixed) | Live cloud URL, security checklist, analytics report | Cloud Security & DP-900 faculty | Fixed |
| Final submission | Fri, Nov 6, 2026 (fixed) | All final submission requirements | All four subject faculty | Fixed |

Only three dates are fixed and unambiguous: Mid Review (Oct 28), Security Check (Nov 3) and Final Submission (Nov 6). All phase planning below is anchored to these three fixed dates; Registration and Design Review are treated as already-imminent/near-term checkpoints and should be confirmed first thing.

# 2. Detailed Division of Technical Responsibilities

Ownership rule: each partner owns a comparable mix of implementation, testing, integration, and documentation. Aryan leads backend/database and backend tests; Vanshika leads frontend and frontend/integration tests. Cloud deployment, security verification, analytics validation, and final submission are deliberately split into named sub-deliverables. Estimated effort is a planning baseline and must be updated weekly with actual hours.

| Task | Owner | Support | Dependencies | Est. effort | Deliverable | Acceptance criteria | Target date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Architecture and API contract | Aryan | Vanshika | None | 4h | Architecture outline + API contract skeleton | Both can explain modules and contract; endpoints/schema agreed | Design Review -1d |
| ER diagram, schema & migrations design | Vanshika | Aryan | Architecture outline | 5h | Mermaid ER diagram + CREATE TABLE draft | Schema smoke-tested locally; FKs and constraints validated | Design Review -1d |
| React frontend & responsive UI | Vanshika | Aryan | API contract / mock API | 18h (phased) | Auth, browse, proposal, attendance and dashboard UI | 375/768/1280px checks pass; no console errors | Mid Review |
| FastAPI backend & REST APIs | Aryan | Vanshika | Schema/API contract | 18h (phased) | Core auth, club/event, approval and attendance endpoints | Documented endpoint tests pass with expected status codes | Mid Review |
| JWT authentication & RBAC | Aryan | Vanshika | Backend skeleton + role matrix | 5h | Login/register/refresh and role dependencies | Five-role denial matrix passes; frontend auth flow verified | Mid Review -2d |
| Database integration & seed data | Vanshika | Aryan | Schema finalized | 5h | Alembic migrations + seed script, paired with Aryan review | Seed data loads without constraint errors; repeatable locally | Mid Review -2d |
| Blob Storage upload/download | Aryan | Vanshika | Backend skeleton and upload UI contract | 3h | Private container and validated upload/download API | Round-trip passes; invalid type/oversize rejected | Security Check -5d |
| Redis caching (optional) | Vanshika | Aryan | MVP core stable | 3h (only if time remains) | Cache listing endpoints and invalidation | Hit and invalidation tests pass; skip if MVP is behind | After MVP |
| Analytics SQL views + Power BI | Vanshika | Aryan | Stable schema and seeded data | 6h | SQL views + three dashboards | Every headline metric checked against manual SQL query | Security Check -2d |
| Security controls & threat mitigation | Aryan (implementation); Vanshika (verification) | Each other | Threat register and deployed build | 8h combined, split 4h each baseline | Controls, evidence, and threat-to-test mapping | All high-risk items have passing evidence and independent review | Security Check -1d |
| Testing & debugging | Both: each tests own module; partner writes independent acceptance tests | Each other | Feature code per phase | Ongoing; log actual hours separately | Unit, API, DB, integration and E2E test evidence | CI green; no critical/high defects open at milestone | Continuous |
| Docker, Azure deployment & CI/CD | Aryan: backend/cloud config; Vanshika: frontend build/pipeline + deployment smoke tests | Each other | Both builds ready | 6h combined, split 3h each baseline | Docker Compose, deployment workflows, live URL | HTTPS URL works; /health returns 200; both can redeploy from README | Security Check -2d |
| GitHub management & documentation | Both: each maintains own module docs; Vanshika maintains project board | Each other | Repo created | Ongoing; shared responsibility | README, contribution guide, issues, PRs and changelog | Issues assigned; reviewed PRs; no unreviewed main pushes | Continuous |
| Final report, demo & submission | Aryan: technical architecture/deployment/test evidence; Vanshika: user-flow/report assembly/video; both rehearse | Each other | Milestones complete | 8h combined, target 4h each | Report, demo script/video, submission package | Checklist complete; both independently run tagged build | Final Submission -1d |

# 3. Phase-Wise Execution Plan

Anchored to the three fixed dates: Mid Review Oct 28, Security Check Nov 3, Final Submission Nov 6. Phases 1-2 should start immediately and are time-boxed to the (to-be-confirmed) Registration/Design Review dates.

## Phase 1: Requirements & Repository Setup (Oct 12 – Oct 14)

Aryan:

- Create repository structure, backend skeleton, Docker Compose baseline and Azure resource-group setup

- Draft FastAPI route/schema stubs and document backend setup steps

Vanshika:

- Set up Vite/Tailwind frontend, linting/formatting and frontend build checks

- Draft requirements and architecture diagrams; set up project board and review proposal gaps

Dependencies: None — first phase

Deliverables / acceptance: Repo exists with backend/ frontend/ db/ docs/ tests/ folders; README with setup steps; both can run project locally

Risks & fallback: Risk: scope creep from proposal's 'optional' items. Fallback: lock MVP list per SDD 1.8 before writing any code.

GitHub checkpoint: Both push an initial scaffold commit to main (small, low-risk) directly; from Phase 2 onward all work goes through feature branches + PRs.

## Phase 2: Design Review Preparation (Oct 14 – Design Review date (CONFIRM, tentatively Oct 19))

Aryan:

- Review schema/ER diagram and validate SQL scripts against a local SQL Server container

- Draft STRIDE threat register and role-permission matrix with Vanshika reviewing

Vanshika:

- Own the ER diagram and relational schema draft, incorporating Aryan’s review

- Finalize architecture diagrams and compile the SDD; Aryan supplies/reviews backend, data and security sections

Dependencies: Phase 1 repo/scaffold

Deliverables / acceptance: SDD complete (all 10 sections); ER diagram renders cleanly; threat register has >=10 entries — matches SDD Section 6

Risks & fallback: Risk: date ambiguity causes a missed deadline. Fallback: confirm the exact date within 24h of plan adoption; treat Oct 19 as the working deadline until corrected.

GitHub checkpoint: feature/design-docs branch; PR reviewed by the other partner; merge by end of this phase; tag design-review-v1.

## Phase 3: Database & Backend Foundation (Oct 15 – Oct 19)

Aryan:

- Implement auth endpoints and JWT/RBAC dependencies; write backend unit tests

- Review migrations and seed data for backend compatibility and constraints

Vanshika:

- Implement schema migrations and repeatable synthetic seed script, reviewed by Aryan

- Scaffold React routing/auth context and build login/register pages against the mocked API

Dependencies: Phase 2 schema + API contract

Deliverables / acceptance: POST /auth/register, /login, /refresh working against Azure SQL (or local SQL Server dev instance); frontend can log in and store token

Risks & fallback: Risk: Azure SQL provisioning delays. Fallback: develop against a local SQL Server Docker container first, point to Azure once provisioned.

GitHub checkpoint: feature/auth-backend and feature/auth-frontend branches; cross-review (each reviews the other's PR); merge into develop by Oct 19.

## Phase 4: Frontend & API Integration (Oct 19 – Oct 23)

Aryan:

- Implement club/event CRUD, membership, registration and capacity/deadline checks

- Publish and maintain OpenAPI contract; write API and database integrity tests

Vanshika:

- Build club directory/profile, event listing/detail and registration UI

- Build club-manager dashboard shell and API contract tests against the agreed OpenAPI spec

Dependencies: Phase 3 auth working end-to-end

Deliverables / acceptance: Student can browse clubs/events in the real UI against the real API; registration write confirmed in DB

Risks & fallback: Risk: API contract drift between frontend expectations and backend implementation. Fallback: FastAPI's auto-generated OpenAPI schema is the single source of truth; regenerate frontend types from it whenever a route changes.

GitHub checkpoint: feature/club-api, feature/event-api, feature/browse-ui branches; PR per module; reviewer = other partner; merge by Oct 23; integration checkpoint demo between partners.

## Phase 5: Core Club/Event Lifecycle Implementation (Oct 23 – Oct 27)

Aryan:

- Implement approval workflow and audit-log backend; add authorization and audit tests

- Implement attendance/outcome endpoints and document API behavior

Vanshika:

- Build proposal form and faculty/HOD review screens

- Build attendance and admin dashboard UI; verify the full workflow with seeded test accounts

Dependencies: Phase 4 club/event CRUD stable

Deliverables / acceptance: Full lifecycle path runs end to end: submit proposal -> faculty review -> HOD approval -> club active -> event created -> student registers -> attendance recorded

Risks & fallback: Risk: this is the largest phase — multi-stage approval workflow. Fallback: if behind schedule, ship proposal+approval only (drop EventOutcomes submission) for Mid Review, finish outcomes in Phase 7.

GitHub checkpoint: feature/approval-workflow, feature/attendance branches; PR + review; merge by Oct 27, one day buffer before Mid Review.

## Phase 6: Mid-Review Preparation (Oct 27 – Oct 28)

Aryan:

- Deploy the working build to the shared dev environment and resolve backend blockers

- Write backend/API/DB smoke tests for the selected core feature

Vanshika:

- Run frontend/integration smoke tests and prepare the Mid Review walkthrough

- Update README run instructions and verify them from a clean checkout

Dependencies: Phase 5 lifecycle working

Deliverables / acceptance: MEETS MID REVIEW MILESTONE (Oct 28): repository link + one core feature (event registration -> attendance) demonstrably working end to end

Risks & fallback: Risk: last-minute breakage. Fallback: freeze main the morning of Oct 28; demo from a tagged commit (mid-review-v1), not live-edited code.

GitHub checkpoint: Tag mid-review-v1 on main; both partners verify the tag builds/runs clean before the review.

## Phase 7: Cloud Deployment, File Storage & Analytics (Oct 28 – Oct 31)

Aryan:

- Own Azure SQL/Blob/Key Vault configuration, backend container and backend deployment workflow

- Supply and validate SQL views; review dashboard metrics against source queries

Vanshika:

- Build upload UI and frontend deployment workflow; verify frontend works at the deployed URL

- Build Power BI dashboards and admin analytics widgets, with SQL cross-checks reviewed by Aryan

Dependencies: Mid Review build is stable

Deliverables / acceptance: Backend reachable at a live Azure HTTPS URL; file upload/download round-trips through Blob Storage; 3 Power BI dashboards live against Azure SQL

Risks & fallback: Risk: Azure configuration/firewall issues eat time. Fallback: keep a local Docker Compose fallback demo ready in case live Azure access is flaky on review day.

GitHub checkpoint: feature/deploy-azure, feature/blob-storage, feature/powerbi branches; PR review; merge by Oct 31; release tag cloud-v1.

## Phase 8: Security Verification (Oct 31 – Nov 3)

Aryan:

- Implement backend security controls: rate limiting, upload validation, secret scanning and RBAC fixes

- Run backend-focused authorization/security tests and log findings for joint triage

Vanshika:

- Own the threat-to-evidence checklist and independently verify backend mitigations

- Test HTTPS, response-data exposure, audit-log behavior and frontend security flows; pair with Aryan on findings

Dependencies: Phase 7 live deployment

Deliverables / acceptance: MEETS SECURITY CHECK MILESTONE (Nov 3): live cloud URL + completed security checklist + analytics report, all with evidence

Risks & fallback: Risk: a High-risk item (e.g., RBAC bypass) is found late. Fallback: treat security fixes as higher priority than any remaining optional feature; Redis/ranking features are explicitly expendable here.

GitHub checkpoint: feature/security-hardening branch; PR requires both partners' sign-off (not just one reviewer) given the milestone stakes; merge and tag security-check-v1 by Nov 3.

## Phase 9: Final Testing, Documentation & Submission (Nov 3 – Nov 6)

Aryan:

- Run backend unit/API/database suites, fix backend defects and finalize deployment runbook

- Pair with Vanshika on all-role acceptance tests and co-present the technical demo

Vanshika:

- Compile the report using module evidence supplied by both partners; own UI/user-journey documentation

- Prepare the recorded demo; Aryan prepares deployment/backend segment, and both rehearse the live walkthrough

Dependencies: Phase 8 security sign-off

Deliverables / acceptance: MEETS FINAL SUBMISSION MILESTONE (Nov 6): all items on the checklist in Section 9 complete and verified

Risks & fallback: Risk: scope creep / last-minute feature additions. Fallback: hard feature freeze on Nov 4; only bug fixes allowed after that.

GitHub checkpoint: Feature freeze Nov 4; final PR to main by Nov 5 EOD; tag final-submission-v1; both partners verify the tagged build one final time before Nov 6.

# 4. Git and GitHub Workflow

## 4.1 Repository Structure

clubsphere/
  frontend/        React + Vite + Tailwind app
  backend/         FastAPI app (routers/, services/, models/, schemas/)
  db/              Alembic migrations, raw SQL scripts, seed scripts
  docs/            SDD, execution plan, API docs, threat register, security checklist
  tests/           pytest (unit/integration/api), Playwright/Cypress E2E
  .github/workflows/  CI/CD pipelines
  docker-compose.yml
  .env.example     (never the real .env)

## 4.2 Conventions

| Aspect | Convention |
| --- | --- |
| Branch naming | feature/<area>-<short-desc> (e.g. feature/event-registration), fix/<short-desc>, chore/<short-desc> |
| Commit messages | Conventional-commit style: feat:, fix:, docs:, test:, chore: + short imperative summary |
| Issues | One GitHub Issue per task row in Section 2's table; assigned to the named owner; labeled by phase and area (backend/frontend/db/security) |
| Pushing | Push working, committed changes at least once per working session — never hold uncommitted work until a phase ends |
| Pull requests | Opened as soon as a task's acceptance criteria can be demonstrated, even if small; PR description links the Issue |
| Review | The non-owner partner reviews every PR before merge; for security-critical PRs (Phase 8) both sign off |
| Merging | Squash-merge into develop; develop merges into main at each milestone checkpoint (tags below) |
| DB migrations | Only one partner edits a given Alembic migration at a time; migrations are reviewed by the other partner before merge to avoid schema drift |
| Shared API contracts | FastAPI's auto-generated OpenAPI schema (docs/openapi.json) is committed and diffed in PRs that change routes, so the frontend owner sees contract changes immediately |
| Merge conflicts | Resolved by the author of the conflicting branch, who rebases on latest develop before requesting re-review; never force-push over the other partner's unpushed work |
| Secrets | Real .env files are git-ignored; only .env.example (no real values) is committed; CI runs a secret-scan step on every PR |

## 4.3 Branching & Release Model

main always reflects the last milestone-tagged, demo-ready state. develop is the integration branch where feature branches merge after review. Release checkpoints are tagged directly on main at each milestone: design-review-v1, mid-review-v1, cloud-v1, security-check-v1, final-submission-v1 — giving faculty a stable, citable commit for each review.

## 4.4 Phase-Wise GitHub Checkpoint Table

| Phase | Aryan pushes | Vanshika pushes | Branch / PR | Reviewer | Merge deadline | Validation before merge |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Repo scaffold, Docker skeleton, Azure resource group config | Vite/Tailwind scaffold, lint config | Direct to main (low risk) | N/A (pairing) | Oct 14 | Both can run locally |
| 2 | Schema review + threat register/API details | ER diagram + architecture diagrams + SDD assembly | feature/design-docs | Cross-review | Design Review date | SDD renders cleanly; schema and threat register reviewed by both |
| 3 | Auth backend + backend unit tests | Migrations/seed data + auth frontend pages | feature/auth-backend, feature/auth-frontend, feature/db-seed | Cross-review | Oct 19 | Login works against seeded DB; migrations repeatable |
| 4 | Club/Event API + API/DB tests | Browse UI + contract tests | feature/club-api, feature/event-api, feature/browse-ui | Cross-review | Oct 23 | API tests green; UI shows live data |
| 5 | Approval/Audit APIs + authorization tests | Proposal/attendance/admin UI + workflow integration tests | feature/approval-workflow, feature/attendance | Cross-review | Oct 27 | Full lifecycle path passes manual walkthrough and acceptance tests |
| 6 | Backend smoke tests + integration fixes | Frontend smoke tests + README/clean-checkout verification | Small PRs to develop, then main | Both | Oct 28 AM | Tag mid-review-v1 builds and runs clean |
| 7 | Azure SQL/Blob/backend deploy + CI/CD | Frontend deploy pipeline + Power BI dashboards + upload UI | feature/deploy-azure, feature/blob-storage, feature/powerbi | Cross-review | Oct 31 | Live URL works; dashboards show SQL-validated data |
| 8 | Backend security fixes + RBAC testing | Independent verification + threat evidence checklist | feature/security-hardening | BOTH sign off | Nov 3 | All high-risk items verified by implementer and independent reviewer |
| 9 | Backend fixes, deployment runbook, technical demo segment | Final report, UI guide, recorded demo; joint acceptance testing | Final PR to main | Both | Nov 5 EOD | Checklist complete; both run tagged build and rehearse |

# 5. Tool Recommendations

| Tool | Purpose | Essential / Optional |
| --- | --- | --- |
| VS Code | Primary IDE for both frontend and backend | Essential |
| GitHub Issues & Projects | Task tracking tied directly to Section 2's ownership table; Kanban board per phase | Essential |
| Mermaid (in-editor/VS Code extension or mermaid.live) | Render all architecture/ER/sequence diagrams from this plan and the SDD | Essential |
| diagrams.net (draw.io) | Only if a non-Mermaid visual (e.g. a polished slide-deck diagram) is needed for the presentation | Optional |
| React + Vite + Tailwind CSS | Frontend stack (required) | Essential |
| FastAPI + Pydantic + pytest | Backend stack and test framework (required) | Essential |
| Azure SQL tools (Azure Data Studio / SSMS) + Alembic | Schema inspection and migration management | Essential |
| Azure Blob Storage SDK (azure-storage-blob) | File upload/download integration | Essential |
| Redis tooling (redis-cli / RedisInsight) | Only needed once the optional caching task starts (Phase 7+) | Optional until then |
| Power BI Desktop | Dashboard authoring against Azure SQL views | Essential (for Security Check milestone) |
| Docker & Docker Compose | Local dev parity + container builds for deployment | Essential |
| Postman or Bruno | API contract testing against the SDD Section 4 spec | Essential |
| Azure Portal + Azure CLI / GitHub Actions for Azure deploy | Resource provisioning and CI/CD deployment | Essential |
| Playwright or Cypress | End-to-end testing across roles | Essential (Phase 9), can be deferred earlier |

To avoid losing time on tooling that doesn't move a milestone forward: skip Redis setup entirely until the MVP core (Phases 1-6) is done and working — it is explicitly an optional extension, not a Mid Review requirement. Likewise, do not invest in diagrams.net unless Mermaid output is genuinely insufficient for the final presentation; Mermaid alone satisfies every diagram requirement in the SDD.

# 6. Data Collection and Preparation Plan

| Dataset | Fields | Created by | Source type | Import procedure |
| --- | --- | --- | --- | --- |
| Departments | Name, Code | Vanshika (seed implementation) + Aryan (schema/review) | Synthetic (short authorized list, e.g. CSE/ECE/ME/Design) | Alembic data migration / one-time seed script |
| Demo users (5 roles) | Email, name, role, department, hashed password | Aryan (users/roles) + Vanshika (club content) | Synthetic (team-generated test accounts) | Faker-based Python seed script, run against dev/staging DB |
| Clubs & memberships | Club name, description, status, member list | Vanshika (event content) + Aryan (constraints/review) | Synthetic demo content | Seed script creates ~20 clubs and random memberships respecting UNIQUE(ClubId,UserId) |
| Events & registrations | Title, date, capacity, registrations | Vanshika (seed records) + Aryan (integrity validation) | Synthetic | Seed script creates ~50 events with randomized, capacity-respecting registrations |
| Attendance | Check-in records tied to confirmed registrations | Both: Vanshika supplies realistic examples; Aryan validates upload/security cases | Derived from registrations (synthetic) | Seed script marks a random subset of confirmed registrants present, to produce a realistic attendance-rate spread for Power BI |
| Proposals & approvals | Proposal text, department, decision, comments | Vanshika | Synthetic, written by the team to look realistic | Manually submitted through the app UI during Phase 5, not bulk-seeded, so the full workflow is actually exercised |
| Documents (posters/logos/proposal PDFs) | Sample files under the allow-listed types | Vanshika | Team-created placeholder files | Uploaded via the /uploads endpoint during Phase 7 testing |

Validation & duplicate handling: the seed script runs idempotently (checks for existing rows by unique key before inserting) so it can be re-run safely; database UNIQUE constraints (ClubMemberships, EventRegistrations, Attendance) are the final backstop against duplicates. Privacy: all seed data uses clearly fictitious names/emails (e.g. @demo.clubsphere.test) — no real student PII is used anywhere in the dataset. Any future use of real institutional data would require explicit university data-authorization approval, which is out of scope for this academic submission. This seed dataset is what both the functional test suite and the Power BI dashboards (Section 8 of the SDD) are built against.

# 7. Testing and Integration Ownership

| Test area | Writer | Independent reviewer | Evidence required before milestone |
| --- | --- | --- | --- |
| Unit tests (backend logic) | Aryan | Vanshika | pytest passing in CI, visible in PR checks — before Mid Review |
| API tests (contract) | Vanshika | Aryan | Postman/Bruno collection run report matching SDD Section 4 — before Mid Review |
| Database integrity tests | Vanshika | Aryan | Constraint-violation tests (duplicate reg, over-capacity) passing — before Mid Review |
| Authentication & RBAC tests | Aryan | Vanshika | Parametrized 403-denial matrix across all 5 roles passing — before Security Check |
| Frontend/backend integration | Vanshika | Aryan | Manual end-to-end walkthrough recorded (screenshots/short video) — before Mid Review |
| File upload security | Aryan | Vanshika | Disallowed-type and oversize rejection tests passing — before Security Check |
| Analytics validation | Vanshika | Aryan | Each Power BI metric cross-checked against a manual SQL query, documented in the analytics report — before Security Check |
| Cloud deployment smoke tests | Aryan | Vanshika | /health 200 + core read endpoints reachable at the live Azure URL — before Security Check |
| End-to-end acceptance (all roles) | Both (split journeys) | Each other | Playwright/Cypress suite green across Student/Manager/Faculty/HOD/Admin journeys — before Final Submission |

# 8. Risk Management and Contingency Planning

| Risk | Owner | Mitigation / contingency |
| --- | --- | --- |
| Delayed API integration (frontend blocked on backend) | Aryan (prevent) / Vanshika (flag early) | FastAPI's auto-generated OpenAPI schema is finalized at the end of Phase 2 so the frontend can build against a typed contract/mock before every endpoint is fully implemented |
| Database schema changes mid-project | Aryan (cloud/backend) + Vanshika (frontend pipeline); both validate | All schema changes go through Alembic migrations reviewed by Vanshika; no raw ad-hoc ALTER statements outside migrations |
| Azure configuration problems (firewall, provisioning delays) | Both: Aryan provisions cloud resources; Vanshika verifies deployment from frontend | Start Azure provisioning in Phase 1, not Phase 7; keep a local Docker Compose fallback demo ready at all times |
| Power BI limitations / licensing access | Vanshika (build) + Aryan (SQL metric validation) | Confirm Power BI Service access early (Phase 1); if Service access is unavailable, submit with Power BI Desktop .pbix file plus exported screenshots as fallback evidence |
| Merge conflicts between the two partners | Both | Frequent small PRs (Section 4) rather than large long-lived branches; conflicting-branch author rebases before re-review |
| Insufficient testing time before a milestone | Both | Testing ownership (Section 7) runs in parallel with feature development per phase, not bolted on at the end |
| Scope creep into optional features (recommendations, QR attendance, extra caching) | Both | Hard rule: no optional/post-MVP item (SDD Section 1.8) is started until all MVP tasks for the current phase are acceptance-criteria-complete |
| Ambiguous Registration/Design Review dates causing a missed early deadline | Both | Confirm exact dates with the project lead within 24 hours of adopting this plan; Phase 2 is already time-boxed to the tentative Oct 19 date as a safety margin |

# 9. Final Submission Checklist

| Item | Owner | Status |
| --- | --- | --- |
| All source code merged to main, tagged final-submission-v1 | Both | Pending |
| System Design Document (10 sections, diagrams, ER diagram) | Both (each owns and reviews assigned SDD sections) | Pending |
| Execution plan (this document) kept up to date with actuals | Both (each updates own tasks; Vanshika maintains consolidated plan) | Pending |
| Live cloud URL (frontend + backend) reachable over HTTPS | Aryan (backend) + Vanshika (frontend pipeline verification) | Pending |
| Database scripts (migrations + CREATE TABLE source) in db/ | Aryan (schema/migrations) + Vanshika (review) | Pending |
| ER diagram (Mermaid source + rendered image) | Vanshika (diagram) + Aryan (schema verification) | Pending |
| Threat model / threat register with verification tests | Aryan (technical threat entries) + Vanshika (register assembly) | Pending |
| Security checklist with pass/fail evidence | Vanshika (checklist) + Aryan (mitigation evidence) | Pending |
| Analytics report (Power BI dashboards + SQL cross-check) | Vanshika (dashboards) + Aryan (SQL cross-check) | Pending |
| Testing evidence (CI run links, coverage summary, E2E report) | Both (each supplies evidence for own tests) | Pending |
| Setup/run instructions (README) verified by the other partner from a clean checkout | Both | Pending |
| Demo script + backup recorded demo video | Aryan (technical script) + Vanshika (recording/UI walkthrough) | Pending |
| Feature freeze observed (no new features after Nov 4) | Both | Pending |

Process: feature freeze on Nov 4, 2026. Final pull request to main due Nov 5 EOD, reviewed and merged by both partners. Release tag final-submission-v1 cut immediately after merge. Final verification: both partners independently clone the tagged commit, run it from scratch (docs/README only) and confirm the live URL and one full lifecycle journey work, the morning of Nov 6 before submission.

Workload balancing rule (revised): The 50/50 target is based on total effort and deadline risk, not equal task counts. Each partner must log actual hours against GitHub Issues. At the end of each phase, compare remaining hours and reassign the next independent task if either partner is more than 20% ahead in estimated remaining effort. Neither partner should be the sole owner of both implementation and final verification for a critical feature.